## Domain1
Audit Area | Control Objective | Audit Procedures | Responsible Auditor | Priority | Planned Start Date | Planned End Date | Status | Findings/Notes
IT Strategy | Ensure IT aligns with business goals | Review IT strategy and board minutes | Auditor A | High | 2025-11-01 | 2025-11-03 | Not Started
Risk Management | Ensure IT risks are identified and mitigated | Review risk register and mitigation plans | Auditor A | High | 2025-11-04 | 2025-11-06 | Not Started
Policies & Procedures | Ensure policies are documented and enforced | Review IT policies and compliance reports | Auditor A | Medium | 2025-11-07 | 2025-11-08 | Not Started

## Domain2
Audit Area | Control Objective | Audit Procedures | Responsible Auditor | Priority | Planned Start Date | Planned End Date | Status | Findings/Notes
SDLC | Ensure proper system development lifecycle | Review project documentation and approvals | Auditor B | High | 2025-11-09 | 2025-11-11 | Not Started
Change Management | Ensure changes are authorized and tested | Review change logs and approvals | Auditor B | High | 2025-11-12 | 2025-11-13 | Not Started
Vendor Management | Ensure third-party risks are managed | Review vendor contracts and SLA compliance | Auditor B | Medium | 2025-11-14 | 2025-11-15 | Not Started

## Domain3
Audit Area | Control Objective | Audit Procedures | Responsible Auditor | Priority | Planned Start Date | Planned End Date | Status | Findings/Notes
IT Operations | Ensure efficient and secure operations | Review incident logs and monitoring reports | Auditor C | Medium | 2025-11-16 | 2025-11-17 | Not Started
Backup & Recovery | Ensure data is backed up and recoverable | Test backup restoration and review logs | Auditor C | High | 2025-11-18 | 2025-11-19 | Not Started
Capacity & Performance | Ensure systems meet performance needs | Review capacity planning reports | Auditor C | Low | 2025-11-20 | 2025-11-21 | Not Started

## Domain4
Audit Area | Control Objective | Audit Procedures | Responsible Auditor | Priority | Planned Start Date | Planned End Date | Status | Findings/Notes
Access Controls | Ensure only authorized access | Review user access rights and test samples | Auditor D | High | 2025-11-22 | 2025-11-23 | Not Started
Network Security | Ensure secure network infrastructure | Review firewall configs and vulnerability scans | Auditor D | High | 2025-11-24 | 2025-11-25 | Not Started
Data Protection | Ensure sensitive data is safeguarded | Review encryption and data classification | Auditor D | High | 2025-11-26 | 2025-11-27 | Not Started
Physical Security | Ensure physical access is restricted | Review data center access logs | Auditor D | Medium | 2025-11-28 | 2025-11-29 | Not Started

## Domain5
Audit Area | Control Objective | Audit Procedures | Responsible Auditor | Priority | Planned Start Date | Planned End Date | Status | Findings/Notes
Regulatory Compliance | Ensure compliance with laws/regulations | Review GDPR | SOX | HIPAA compliance | Auditor E | High | 2025-11-30 | 2025-12-01 | Not Started
Business Continuity | Ensure continuity of operations | Review BCP/DRP test results | Auditor E | High | 2025-12-02 | 2025-12-03 | Not Started
Incident Response | Ensure incidents are managed effectively | Review incident response plan and test results | Auditor E | Medium | 2025-12-04 | 2025-12-05 | Not Started